## sheet1
Scheduled? | Run Date | SO # | SOL ID | Finished Item | Description | Customer | avg_num_employees | Total QTY | Produced QTY | Remaining QTY | Due Date | EQP Code | Priority Status | person hour rate | Tool # | Ticket Color | Everything at STF | order entry date | Customer Supplied Component | 34-QPB4 | bag quantity | ELC label | bag_indicator | label_indicator | warehouse_name | location | In progress | Picked
N |  | M538039 | 97223 | 24 050 13-S1 | FUEL FILTER - KOHLER | DISCOVERY ENERGY LLC | 8 | 8304 | 6300 | 2004 | 2026-03-25 | 6ST | P | 228.8903 | 307 | Yellow | N | 2026-02-24 09:00 |  |  | 0 | 80.16 |  |  | SF | St Francis
N |  | M537914 | 97002 | GP1043211-VS | SIMPLICE SPRAYHEAD | Kohler Plumbing | 5 | 3900 | 2313 | 1587 | 2026-03-27 | STF-SMB | + | 128.3877 | 3025 | Green | Y | 2026-02-19 15:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M538558-1 | 98570 | 85406-PB | PARTS BAG FOR 85406 | QPI | 2 | 960 | 0 | 960 | 2026-04-01 | AB/ABM | + | 109.3277 |  | White | Y | 2026-03-19 09:19 |  |  | 0 |  |  |  | SF | Morris
N |  | M538334 | 97704 | 70-0091-2618-9 | 414H-DC-EF EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 4800 | 0 | 4800 | 2026-04-02 | STF-20S-L-BR |  | 242.449 | 367 | Green | Y | 2026-03-04 14:30 |  | 34-8728-9151-9-QPB4 | 0 | 399.84 |  | Y | SF | St Francis
N |  | M539204 | 98943 | 70-0069-3426-2 | 200NA Electrical Tp,0.75inX12.5yd, 24/cs | 3M ELECTRICAL TAPE | 8 | 6048 | 0 | 6048 | 2026-04-06 | STF-16ST |  | 231.0301 | 402 | Green | Y | 2026-03-26 16:49 |  |  | 1008.2016 |  | Y |  | SF | St Francis
N |  | M538534 | 97992 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 15600 | 6000 | 9600 | 2026-04-07 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-03-10 09:39 |  | 34-8728-9151-9-QPB4 | 0 | 799.68 |  | Y | SF | St Francis
N |  | M538591 | 98080 | 70-0091-8635-7 | 17051BNB-2ESAZ Trad Med Hk WR Str | 3M ACCOUNTS PAYABLE | 8 | 1848 | 0 | 1848 | 2026-04-07 | STF-8ST | P | 140.7559 | SEAL TOOL ID, ALGUS 2014 | Green | Y | 2026-03-11 09:41 |  |  | 0 | 65.9736 |  |  | SF | St Francis
N |  | M538670 | 98194 | RGP77006-RP | VALVE KIT - RF | Kohler Plumbing | 10 | 2000 | 1581 | 419 | 2026-04-07 | RF | P | 46.3863 | T6-008 | Green | Y | 2026-03-12 10:00 |  |  | 0 |  |  |  | SF | St Francis |  | STF-RF
N |  | M538688 | 98228 | GP1112256 | 2' TOILET GASKET | Kohler Plumbing | 5 | 1000 | 0 | 1000 | 2026-04-07 | STF-SMB | P | 155.922 | 3067 | Green | Y | 2026-03-12 15:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539293 | 99059 | 70-0069-3426-2 | 200NA Electrical Tp,0.75inX12.5yd, 24/cs | 3M ELECTRICAL TAPE | 8 | 6048 | 0 | 6048 | 2026-04-08 | STF-16ST |  | 231.0301 | 402 | Green | Y | 2026-03-30 10:18 |  |  | 1008.2016 |  | Y |  | SF | St Francis
N |  | M538651 | 98175 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 12000 | 0 | 12000 | 2026-04-09 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-03-12 09:55 |  | 34-8728-9151-9-QPB4 | 0 | 999.6 |  | Y | SF | St Francis
N |  | M538827 | 98433 | 70-0091-8640-7 | 17005-ES Spring Clip | 3M ACCOUNTS PAYABLE | 11 | 2160 | 0 | 2160 | 2026-04-10 | STF-8ST |  | 162.9434 | SEAL TOOL ID, ALGUS 1081 | Green | Y | 2026-03-17 16:27 |  |  | 358.56 | 118.8 | Y |  | SF | St Francis
N |  | M539456 | 99256 | 70-0069-3429-6 | 16736NA Cld WthrElecTp 0.75inX25ft 24/cs | 3M ELECTRICAL TAPE | 9 | 16800 | 0 | 16800 | 2026-04-10 | STF-16ST |  | 337.9572 | 403 | White | N | 2026-04-01 16:07 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539913 | 99977 | 70-0091-2504-1-SUB | 314S-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M ACCOUNTS PAYABLE | 11 | 14000 | 0 | 14000 | 2026-04-10 | STF-16ST | + | 245.2869 | 372 | Yellow | N | 2026-04-13 09:33 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M538737 | 98276 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 0 | 8400 | 2026-04-13 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-03-13 08:59 |  | 34-8727-4490-8-QPB4 | 0 | 699.72 |  | Y | SF | St Francis
N |  | M538842 | 98449 | GP75878 | DIVERTER ASSY KOH PLUMB | Kohler Plumbing | 5 | 500 | 0 | 500 | 2026-04-13 | STF-SMB | P | 166.9565 | 1011 | Green | Y | 2026-03-18 10:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539429 | 99225 | 24 786 10-PB | PARTS BAG 24 786 10-S | DISCOVERY ENERGY LLC | 2 | 72 | 0 | 72 | 2026-04-13 | AB/ABM |  | 54.0727 |  | Green | N | 2026-03-31 15:23 |  |  | 0 |  |  |  | SF | Morris
N |  | M539430 | 99226 | 24 786 12-PB | PARTS BAG 24 786 12-S | DISCOVERY ENERGY LLC | 2 | 80 | 0 | 80 | 2026-04-13 | AB/ABM |  | 71.6 |  | Green | N | 2026-03-31 15:24 |  |  | 0 |  |  |  | SF | Morris
N |  | M539490 | 99298 | 70-0069-3413-0 | 03744NA Spr 33+ Eltcl Tp .75X300in 24/cs | 3M AUTO TAPE | 11 | 1224 | 0 | 1224 | 2026-04-13 | STF-16ST |  | 264.8421 | 403 | Pink | Y | 2026-04-02 09:53 |  | 34-8722-8091-1-QPB4 | 0 |  |  |  | SF | St Francis
N |  | M538649 | 98173 | 70-0069-3413-0 | 03744NA Spr 33+ Eltcl Tp .75X300in 24/cs | 3M ELECTRICAL TAPE | 11 | 1224 | 0 | 1224 | 2026-04-14 | STF-16ST |  | 264.8421 | 403 | Pink | Y | 2026-03-12 09:55 |  | 34-8722-8091-1-QPB4 | 0 |  |  |  | SF | St Francis
N |  | M538870 | 98478 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 12000 | 0 | 12000 | 2026-04-14 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8728-9151-9-QPB4 | 0 | 999.6 |  | Y | SF | St Francis
N |  | M538871 | 98479 | 70-0091-1386-4 | 414H EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 13920 | 10440 | 3480 | 2026-04-14 | STF-20S-L-BS |  | 283.4888 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8728-9151-9-QPB4 | 580.116 | 289.884 | Y | Y | SF | St Francis
N |  | M538873 | 98481 | 70-0091-1777-4 | 414H-48 EXTREME DS MTG TAPE 1IN X 48 IN | 3M SCOTCH | 11 | 3480 | 0 | 3480 | 2026-04-14 | STF-20S-L-BS |  | 227.36 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8728-0901-6-QPB4 | 580.116 | 289.884 | Y |  | SF | St Francis
N |  | M538875 | 98483 | 70-0091-2500-9 | 410S Clear DS MTG Tape 1in x 60in | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-04-14 | STF-20S-L-BS |  | 322.7027 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8727-4490-8-QPB4 | 600.12 | 299.88 | Y | Y | SF | St Francis
N |  | M538879 | 98487 | 70-0091-2507-4 | 410H CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 6960 | 0 | 6960 | 2026-04-14 | STF-20S-L-BS |  | 227.0665 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8727-4490-8-QPB4 | 1160.232 | 579.768 | Y | Y | SF | St Francis
N |  | M538880 | 98488 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 2400 | 6000 | 2026-04-14 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8727-4490-8-QPB4 | 0 | 499.8 |  | Y | SF | St Francis
N |  | M538881 | 98489 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 12000 | 0 | 12000 | 2026-04-14 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8727-4490-8-QPB4 | 0 | 999.6 |  | Y | SF | St Francis
N |  | M538884 | 98492 | 70-0091-2618-9 | 414H-DC-EF EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 4800 | 0 | 4800 | 2026-04-14 | STF-20S-L-BR |  | 242.449 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8728-9151-9-QPB4 | 0 | 399.84 |  | Y | SF | St Francis
N |  | M538885 | 98493 | 70-0091-2621-3 | 410H-DC-EF CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 2400 | 0 | 2400 | 2026-04-14 | STF-20S-L-BR |  | 250.4065 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8727-4490-8-QPB4 | 0 | 199.92 |  | Y | SF | St Francis
N |  | M538886 | 98494 | 70-0091-2657-7 | 410S-SR CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-04-14 | STF-20S-L-BR |  | 277.2 | 367 | Green | Y | 2026-03-18 12:20 |  | 34-8727-4490-8-QPB4 | 0 | 168.1344 |  | Y | SF | St Francis
N |  | M538887 | 98495 | 70-0091-2714-6 | 114S Indoor DS MTG Tape 1 in x 50 in | 3M SCOTCH | 11 | 14400 | 0 | 14400 | 2026-04-14 | STF-20S-L-BS |  | 282.7925 | 367 | Green | Y | 2026-03-18 12:21 |  | 34-8727-2939-6-QPB4 | 2400.48 | 1199.52 | Y | Y | SF | St Francis
N |  | M539489 | 99297 | 60-4550-5682-4 | PN03439 CLEAR REPAIR TAPE 1.5 IN X 115 IN 24/CASE V11 | 3M AUTO TAPE | 11 | 2160 | 0 | 2160 | 2026-04-14 | STF-16ST | + | 246.8571 | 404 | Yellow | Y | 2026-04-02 09:53 |  |  | 0 | 179.928 |  |  | SF | St Francis
N |  | M539545 | 99377 | 70-0069-3429-6 | 16736NA Cld WthrElecTp 0.75inX25ft 24/cs | 3M ELECTRICAL TAPE | 9 | 16800 | 0 | 16800 | 2026-04-14 | STF-16ST |  | 337.9572 | 403 | Pink | N | 2026-04-03 10:16 |  |  | 0 |  |  |  | SF | St Francis
N |  | M538943 | 98594 | 18 883 01-S1 | AIR FILTER/PRE-CLEANER KIT | DISCOVERY ENERGY LLC | 5 | 2880 | 0 | 2880 | 2026-04-15 | STF-SMB |  | 142.3155 |  | Green | Y | 2026-03-19 14:00 |  |  | 0 | 288 |  |  | SF | St Francis
N |  | M538950 | 98603 | 32 083 14-S | ELEMENT PRE CLEANER | DISCOVERY ENERGY LLC | 2 | 1800 | 0 | 1800 | 2026-04-15 | AB |  | 196 |  | Green | Y | 2026-03-19 18:00 |  |  | 0 | 180 |  |  | SF | St Francis
N |  | M539604 | 99462 | 70-0091-7155-7-N | SF400C-DC-5-M SFTY GGL CLR AF 5EA CV | 3M EYEWEAR | 11 | 1200 | 0 | 1200 | 2026-04-15 | STF-16ST |  | 848.9796 | 460 | White | N | 2026-04-06 10:41 |  | 34-2001-6495-1-QPB4 | 0 | 480 |  |  | SF | St Francis
N |  | M538186 | 97470 | 70-0091-1034-0-N | 47212H1-VDC GRY RED CLR AF 5 CASE | 3M EYEWEAR | 11 | 13760 | 0 | 13760 | 2026-04-16 | STF-16ST |  | 105.7863 | 458 | Green | Y | 2026-03-02 11:05 |  | 34-2001-7183-2-QPB4 | 0 | 5504 |  |  | SF | St Francis |  | STF-16ST-A
N |  | M539121 | 98812 | 70-0091-3481-1 | 410S-ESF CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 7200 | 0 | 7200 | 2026-04-16 | STF-20S-L-BS |  | 263.2104 | 367 | Yellow | N | 2026-03-25 09:45 |  | 34-8727-4490-8-QPB4 | 1200.24 | 599.76 | Y | Y | SF | St Francis
N |  | M538831 | 98437 | 70-0092-1238-5 | 17065CLR-6ESBOBU | 3M ACCOUNTS PAYABLE | Bhargav | 24000 | 0 | 24000 | 2026-04-17 | STF-8ST |  | 71.7597 |  | Green | N | 2026-03-17 16:43 |  |  | 0 | 307.2 |  |  | SF | St Francis
N |  | M538957 | 98610 | 70-0091-6631-8 | FC13-BN-EF Large Brushed Nickel | 3M ACCOUNTS PAYABLE | 11 | 1152 | 0 | 1152 | 2026-04-17 | STF-8ST |  | 112.3902 | 2551 | Green | Y | 2026-03-20 09:36 |  |  | 288 | 144 | Y |  | SF | St Francis
N |  | M539023 | 98707 | 70-0091-9118-3 | 17051BNB-2ESF TRAD MD HK W/WTR RES ST | 3M ACCOUNTS PAYABLE | 11 | 14400 | 13200 | 1200 | 2026-04-17 | STF-8ST |  | 136.2286 | 2014 | Green | Y | 2026-03-23 15:01 |  |  | 600 | 99.96 | Y |  | SF | St Francis
N |  | M539031 | 98715 | 70-0091-6528-6 | FC13-ORB-ES Forever Classic Large Hook | 3M ACCOUNTS PAYABLE | 11 | 9600 | 0 | 9600 | 2026-04-17 | STF-8ST |  | 188.3858 | 2551 | Green | Y | 2026-03-23 15:01 |  |  | 2400 | 960 | Y |  | SF | St Francis
N |  | M539091 | 98775 | GP800881 | CARTRIDGE SINGLE SEQUENTIAL | Kohler Plumbing | 6 | 2800 | 0 | 2800 | 2026-04-17 | STF-SMB | + | 125.2857 | 077 | Green | Y | 2026-03-24 11:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539663 | 99553 | 70-0069-3426-2 | 200NA Electrical Tp,0.75inX12.5yd, 24/cs | 3M ELECTRICAL TAPE | 8 | 6048 | 0 | 6048 | 2026-04-17 | STF-16ST |  | 231.0301 | 402 | Green | Y | 2026-04-07 08:40 |  |  | 1008.2016 |  | Y |  | SF | St Francis
N |  | M539728 | 99651 | 70-0091-7137-5-N | 47013H1-DC-M BLK YLW AMBER LENS 5 CV | 3M EYEWEAR | 11 | 600 | 0 | 600 | 2026-04-17 | STF-16ST |  | 70.5882 | 460 | Green | Y | 2026-04-08 09:29 |  | 34-2001-6583-4-QPB4 | 0 | 240 |  |  | SF | St Francis
N |  | M537322 | 96075 | 70-0069-5847-7 | RF7053 Indoor Fasteners | 3M SCOTCH | 14 | 3840 | 0 | 3840 | 2026-04-20 | STF-16ST |  | 101.6869 | 424 | White | N | 2026-02-04 10:20 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M538960 | 98613 | 70-0091-2858-1 | 114S-ESF Indoor DS MTG Tape 1in x 50in | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-04-20 | STF-20S-L-BS |  | 245.3664 | 367 | Green | N | 2026-03-20 09:36 |  | 34-8727-2939-6-QPB4 | 600.12 | 299.88 | Y | Y | SF | St Francis
N |  | M538961 | 98614 | 70-0091-1388-0 | 214H Indoor DS MTG Tape 1in x 55in | 3M SCOTCH | 11 | 20880 | 0 | 20880 | 2026-04-20 | STF-20S-L-BR |  | 271.1143 | 367 | Green | Y | 2026-03-20 09:36 |  | 34-8727-2939-6-QPB4 | 3480.696 | 1739.304 | Y | Y | SF | St Francis
N |  | M539397 | 99186 | 70-0069-5847-7 | RF7053 Indoor Fasteners | 3M SCOTCH | 14 | 3840 | 0 | 3840 | 2026-04-20 | STF-16ST |  | 101.6869 | 424 | White | N | 2026-03-31 08:54 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539496-1 | 99321 | 85406-PB | PARTS BAG FOR 85406 | QPI | 2 | 960 | 0 | 960 | 2026-04-20 | AB/ABM | + | 109.3277 |  | White | Y | 2026-04-02 13:33 |  |  | 0 |  |  |  | SF | Morris
N |  | M539771 | 99708 | 70-0069-3413-0 | 03744NA Spr 33+ Eltcl Tp .75X300in 24/cs | 3M ELECTRICAL TAPE | 11 | 1224 | 0 | 1224 | 2026-04-20 | STF-16ST |  | 264.8421 | 403 | Pink | Y | 2026-04-09 09:45 |  | 34-8722-8091-1-QPB4 | 0 |  |  |  | SF | St Francis
N |  | M539772 | 99709 | 70-0069-3413-0 | 03744NA Spr 33+ Eltcl Tp .75X300in 24/cs | 3M ELECTRICAL TAPE | 11 | 1224 | 0 | 1224 | 2026-04-20 | STF-16ST |  | 264.8421 | 403 | Pink | Y | 2026-04-09 09:45 |  | 34-8722-8091-1-QPB4 | 0 |  |  |  | SF | St Francis
N |  | M539773 | 99710 | 60-4550-6440-6 | PN04862 3M MULTI-PURPOSE FASTENERS 4 PACK 24/CASE V11 | 3M AUTO TAPE | 11 | 8232 | 0 | 8232 | 2026-04-20 | STF-16ST |  | 120.4865 | TOOL ID 411 | Yellow | N | 2026-04-09 09:45 |  | 34-8708-9387-1-QPB4 | 0 |  |  |  | SF | St Francis
N |  | M538150 | 97427 | 70-0069-3429-6 | 16736NA Cld WthrElecTp 0.75inX25ft 24/cs | 3M ELECTRICAL TAPE | 9 | 16800 | 0 | 16800 | 2026-04-21 | STF-16ST |  | 337.9572 | 403 | Pink | N | 2026-02-27 09:08 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539033 | 98717 | 60-4551-0996-1 | 3M Red Lens Repair Tape, 3441SRP, 1.875 in x 60 in, 4/case | 3M AUTO TAPE | 14 | 5488 | 0 | 5488 | 2026-04-21 | STF-16ST |  | 135.7668 | 404 | Yellow | N | 2026-03-23 15:01 |  | 34-8724-9244-1-QPB4 | 0 | 10976 |  |  | SF | St Francis
N |  | M539038 | 98722 | 70-0091-2714-6 | 114S Indoor DS MTG Tape 1 in x 50 in | 3M SCOTCH | 11 | 14400 | 0 | 14400 | 2026-04-21 | STF-20S-L-BS |  | 282.7925 | 367 | Green | Y | 2026-03-23 15:01 |  | 34-8727-2939-6-QPB4 | 2400.48 | 1199.52 | Y | Y | SF | St Francis
N |  | M539039 | 98723 | 70-0069-6048-1 | 214P-CFT INDOOR MOUNTING TAPE | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-04-21 | STF-16ST |  | 158.2418 | 378 | Green | Y | 2026-03-23 15:01 |  |  | 900 | 299.88 | Y |  | SF | St Francis
N |  | M539042 | 98726 | 70-0091-2504-1 | 314S-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 8640 | 0 | 8640 | 2026-04-21 | STF-16ST |  | 193.7104 | 372 | Yellow | N | 2026-03-23 15:01 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M539044 | 98728 | 70-0091-2507-4 | 410H CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 6960 | 0 | 6960 | 2026-04-21 | STF-20S-L-BS |  | 227.0665 | 367 | Green | Y | 2026-03-23 15:01 |  | 34-8727-4490-8-QPB4 | 1160.232 | 579.768 | Y | Y | SF | St Francis
N |  | M539045 | 98729 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 9600 | 0 | 9600 | 2026-04-21 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-03-23 15:01 |  | 34-8727-4490-8-QPB4 | 0 | 799.68 |  | Y | SF | St Francis
N |  | M539047 | 98731 | 70-0091-2657-7 | 410S-SR CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-04-21 | STF-20S-L-BR |  | 277.2 | 367 | Green | Y | 2026-03-23 15:01 |  | 34-8727-4490-8-QPB4 | 0 | 168.1344 |  | Y | SF | St Francis
N |  | M539048 | 98732 | 70-0091-1777-4 | 414H-48 EXTREME DS MTG TAPE 1IN X 48 IN | 3M SCOTCH | 11 | 6960 | 0 | 6960 | 2026-04-21 | STF-20S-L-BS |  | 227.36 | 367 | Green | Y | 2026-03-23 15:01 |  | 34-8728-0901-6-QPB4 | 1160.232 | 579.768 | Y |  | SF | St Francis
N |  | M539050 | 98734 | 70-0069-9274-0 | RF7020X SCOTCH(R) INDOOR FASTENERS | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-04-21 | STF-16ST |  | 157.5426 | 424 | Green | Y | 2026-03-23 15:01 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539051 | 98735 | 70-0050-3227-4 | RF7021 MLT-PRPS FSTENRS, 7/8 IN X 7/8 IN | 3M SCOTCH | 11 | 6720 | 0 | 6720 | 2026-04-21 | STF-16ST |  | 210.1425 | 424 | Yellow | N | 2026-03-23 15:01 |  |  | 1680 | 559.776 | Y |  | SF | St Francis
N |  | M539081 | 98765 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 20400 | 0 | 20400 | 2026-04-21 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-03-24 10:01 |  | 34-8728-9151-9-QPB4 | 0 | 1699.32 |  | Y | SF | St Francis
N |  | M539190 | 98920 | GP83996 | GASKET FLUSH VALVE | Kohler Plumbing | 5 | 2000 | 0 | 2000 | 2026-04-21 | STF-SMB |  | 120.0717 | 1011 | Green | Y | 2026-03-26 10:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539191 | 98921 | GP800881 | CARTRIDGE SINGLE SEQUENTIAL | Kohler Plumbing | 6 | 1200 | 0 | 1200 | 2026-04-21 | STF-SMB | + | 125.2857 | 077 | Green | Y | 2026-03-26 10:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539192 | 98922 | GP1142713-CP | TRIP LEVER KIT | Kohler Plumbing | 5 | 1000 | 0 | 1000 | 2026-04-21 | STF-SMB | P | 93.8052 | 17QP0033A3/ TOOL ID 149 | Green | Y | 2026-03-26 10:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539857 | 99907 | 70-0069-3428-8 | 194NA Spr 33+ElcTp,.5 in X 5.5 yd, 24/cs | 3M ELECTRICAL TAPE | 11 | 1728 | 0 | 1728 | 2026-04-21 | STF-16ST |  | 192.5944 | 406 | White | N | 2026-04-10 16:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539858 | 99908 | 60-4551-0996-1 | 3M Red Lens Repair Tape, 3441SRP, 1.875 in x 60 in, 4/case | 3M AUTO TAPE | 14 | 4116 | 0 | 4116 | 2026-04-21 | STF-16ST |  | 135.7668 | 404 | Yellow | N | 2026-04-10 16:00 |  | 34-8724-9244-1-QPB4 | 0 | 8232 |  |  | SF | St Francis
N |  | M538953 | 98606 | 12 050 01-S1 | SMALL OIL FILTER | DISCOVERY ENERGY LLC | 11 | 17280 | 0 | 17280 | 2026-04-22 | STF-16ST-A | + | 151.9715 | DE T2070 | Green | Y | 2026-03-20 09:00 |  |  | 0 | 864 |  |  | SF | St Francis
N |  | M539221 | 98968 | GP1144925 | CARTRIDGE HIGHFLOW PBU | Kohler Plumbing | 6 | 500 | 485 | 15 | 2026-04-22 | STF-SMB | + | 78.1667 | TOOL#0108J66594 | Green | Y | 2026-03-27 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539224 | 98971 | RGP77759 | MIXER CAP KIT | Kohler Plumbing | 10 | 2016 | 0 | 2016 | 2026-04-22 | RF | + | 30.5904 | T6-013 | Green | Y | 2026-03-27 10:00 |  |  | 0 | 665.28 |  |  | SF | St Francis
N |  | M539243 | 98990 | GP1018165-F | DRY LOCK GASKET | Kohler Plumbing | 5 | 4938 | 1440 | 3498 | 2026-04-22 | STF-LMB |  | 126.4254 | QPI 1011 | White | Y | 2026-03-27 11:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539257 | 99004 | 25 041 10-S | GASKET | DISCOVERY ENERGY LLC | 2 | 150 | 0 | 150 | 2026-04-22 | AB/ABM |  | 300 |  | Green | Y | 2026-03-27 15:00 |  |  | 0 | 3 |  |  | SF | Morris
N |  | M539264 | 99011 | 14 083 01-S1 | AIR FILTER - KOH ENG | DISCOVERY ENERGY LLC | 5 | 2400 | 0 | 2400 | 2026-04-22 | STF-SMB |  | 136.017 |  | Yellow | N | 2026-03-27 15:01 |  |  | 0 | 240 |  |  | SF | St Francis
N |  | M539268 | 99015 | 24 123 22-S | KIT OIL FILL TUBE | DISCOVERY ENERGY LLC | 2 | 180 | 0 | 180 | 2026-04-22 | AB |  | 33.1111 |  | Green | Y | 2026-03-27 15:01 |  |  | 0 |  |  |  | SF | Morris
N |  | M539271 | 99018 | 25 132 28-S | PLUG SPARK | DISCOVERY ENERGY LLC | 2 | 1000 | 0 | 1000 | 2026-04-22 | AB/ABM |  | 122.4489 |  | Green | Y | 2026-03-27 15:01 |  |  | 0 | 50 |  |  | SF | Morris
N |  | M539879 | 99943 | 60-4551-0996-1 | 3M Red Lens Repair Tape, 3441SRP, 1.875 in x 60 in, 4/case | 3M AUTO TAPE | 14 | 4116 | 0 | 4116 | 2026-04-22 | STF-16ST |  | 135.7668 | 404 | Yellow | N | 2026-04-13 09:32 |  | 34-8724-9244-1-QPB4 | 0 | 8232 |  |  | SF | St Francis
N |  | M539880 | 99944 | 70-0091-7140-9 | 47030H1-DC-M EYE PROTECT CLR CLR AS 5 CV | 3M EYEWEAR | 11 | 480 | 0 | 480 | 2026-04-22 | STF-16ST |  | 132.5714 | 399 | Green | Y | 2026-04-13 09:32 |  | 34-8709-7729-4-QPB4 | 0 | 96 |  |  | SF | St Francis
N |  | M539883 | 99947 | 70-0091-7157-3-N | SF400G-DC-5-M SFTY EYE GRAY AF 5EA CV | 3M EYEWEAR | 11 | 1200 | 0 | 1200 | 2026-04-22 | STF-16ST |  | 70.8376 | 460 | Green | Y | 2026-04-13 09:33 |  | 34-2001-6496-9-QPB4 | 0 | 480 |  |  | SF | St Francis
N |  | M539884 | 99948 | 70-0091-7153-2-N | 47212-DC-4-M SFT GGL GRAY RED CLEAR 4 CV | 3M EYEWEAR | 11 | 1900 | 0 | 1900 | 2026-04-22 | STF-16ST |  | 57.6043 | 458 | Green | Y | 2026-04-13 09:33 |  | 34-2001-7183-2-QPB4 | 0 | 950 |  |  | SF | St Francis
N |  | M539885 | 99949 | 70-0091-1034-0-N | 47212H1-VDC GRY RED CLR AF 5 CASE | 3M EYEWEAR | 11 | 13760 | 0 | 13760 | 2026-04-22 | STF-16ST |  | 105.7863 | 458 | Green | Y | 2026-04-13 09:33 |  | 34-2001-7183-2-QPB4 | 0 | 5504 |  |  | SF | St Francis
N |  | M539886 | 99950 | 70-0069-3410-6 | 03429NA 700 Elctrcl Tp, .75inX66ft 24/cs | 3M ELECTRICAL TAPE | 10 | 3600 | 0 | 3600 | 2026-04-22 | STF-16ST |  | 268.9727 | 409 | Green | Y | 2026-04-13 09:33 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539887 | 99951 | 70-0069-3436-1 | 10455NA Spr 33+ Elctrcl Tape 24/cs | 3M ELECTRICAL TAPE | 11 | 1200 | 0 | 1200 | 2026-04-22 | STF-16ST |  | 118.8811 | 407 | Green | Y | 2026-04-13 09:33 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539896 | 99960 | 70-0069-5849-3 | RF7060 Indoor Fasteners | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-04-22 | STF-16ST |  | 166.9762 | 424 | Green | N | 2026-04-13 09:33 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539897 | 99961 | 70-0069-6055-6 | RF7170X-ALT INDOOR FASTENERS | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-04-22 | STF-16ST |  | 106.2966 | 424 | Green | N | 2026-04-13 09:33 |  |  | 756 | 504.1008 | Y |  | SF | St Francis
N |  | M539903 | 99967 | 70-0091-1389-8 | 214H-DC Indoor DS MTG Tape 1in x 55in | 3M SCOTCH | 12 | 9600 | 0 | 9600 | 2026-04-22 | STF-20S-L-BR |  | 305.6 | 367 | Green | Y | 2026-04-13 09:33 |  | 34-8727-2939-6-QPB4 | 0 | 799.68 |  | Y | SF | St Francis
N |  | M539904 | 99968 | 70-0091-1777-4 | 414H-48 EXTREME DS MTG TAPE 1IN X 48 IN | 3M SCOTCH | 11 | 3480 | 0 | 3480 | 2026-04-22 | STF-20S-L-BS |  | 227.36 | 367 | Green | Y | 2026-04-13 09:33 |  | 34-8728-0901-6-QPB4 | 580.116 | 289.884 | Y |  | SF | St Francis
N |  | M539914 | 99978 | 70-0091-6594-8 | 17036MB-VPES Matte Black Hooks Combo Pck | 3M ACCOUNTS PAYABLE | 11 | 960 | 0 | 960 | 2026-04-22 | STF-16ST |  | 76.8511 | Seal Tool ID: 452 | Green | Y | 2026-04-13 09:33 |  |  | 240 | 79.968 | Y |  | SF | St Francis
N |  | M539915 | 99979 | 70-0091-6543-5 | FC13-BN-2ES Lg Frv Clsc BN Met Hk, 2 pk | 3M ACCOUNTS PAYABLE | 11 | 4608 | 0 | 4608 | 2026-04-22 | STF-8ST |  | 119.5828 | 2600 | Green | N | 2026-04-13 09:33 |  |  | 1152 | 576 | Y |  | SF | St Francis
N |  | M539916 | 99980 | 70-0091-6554-2 | FC13-ORB-2ES Lg Fv Cl OR Brz Mt Hk, 2 pk | 3M ACCOUNTS PAYABLE | 11 | 3072 | 0 | 3072 | 2026-04-22 | STF-8ST |  | 99.0968 | 2600 | Green | Y | 2026-04-13 09:33 |  |  | 768 | 384 | Y |  |  | St Francis
N |  | M539917 | 99981 | 70-0091-6610-2 | MR02-BN-ES Modern Ref Med Hook | 3M ACCOUNTS PAYABLE | 11 | 4480 | 0 | 4480 | 2026-04-22 | STF-8ST |  | 205.6205 | 2550 | Green | Y | 2026-04-13 09:33 |  |  | 1120 | 560 | Y |  |  | St Francis
N |  | M539919 | 99983 | 70-0091-9124-1 | 17051BN-B-ESF Traditional Medium Hook | 3M ACCOUNTS PAYABLE | 11 | 2016 | 0 | 2016 | 2026-04-22 | STF-8ST |  | 141.5798 | 1951 | Green | Y | 2026-04-13 09:33 |  |  | 504 | 167.328 | Y |  | SF | St Francis
N |  | M539122 | 98813 | 70-0069-5849-3 | RF7060 Indoor Fasteners | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-04-23 | STF-16ST |  | 166.9762 | 424 | Green | N | 2026-03-25 09:45 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539123 | 98814 | 70-0091-2504-1 | 314S-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 12960 | 0 | 12960 | 2026-04-23 | STF-16ST |  | 193.7104 | 372 | Yellow | N | 2026-03-25 09:45 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M539205 | 98944 | 70-0069-6055-6 | RF7170X-ALT INDOOR FASTENERS | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-04-23 | STF-16ST |  | 106.2966 | 424 | Green | N | 2026-03-26 16:49 |  |  | 756 | 504.1008 | Y |  | SF | St Francis
N |  | M539206 | 98945 | 70-0091-2710-4 | 414S-48 EXTREME DS MTG TAPE 1IN 48IN | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-04-23 | STF-20S-L-BS |  | 257.3055 | 367 | Green | Y | 2026-03-26 16:49 |  | 34-8728-0901-6-QPB4 | 600.12 | 299.88 | Y |  | SF | St Francis
N |  | M539232 | 98979 | 70-0091-2501-7 | 110S INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 18000 | 0 | 18000 | 2026-04-23 | STF-16ST |  | 276.0821 | 374 | Yellow | N | 2026-03-27 10:10 |  | 34-8727-2939-6-QPB4 | 3000.6 |  | Y | Y | SF | St Francis
N |  | M539235 | 98982 | 70-0091-2712-0 | 859S-SR REMOVABLE DS MTG SQUARES | 3M SCOTCH | 11 | 10368 | 0 | 10368 | 2026-04-23 | STF-16ST |  | 190.8517 | 376 | Green | Y | 2026-03-27 10:10 |  |  | 0 |  |  |  | SF | St Francis
N |  | M538894 | 98502 | 70-0092-0332-7 | 47317 Sfty Eyewear Mirror, multi, 6 ea/cv | 3M ACCOUNTS PAYABLE | 11 | 4800 | 0 | 4800 | 2026-04-24 | STF-16ST |  | 100 | 458 | Pink | N | 2026-03-18 12:21 |  |  | 0 | 1599.84 |  |  | SF | St Francis
N |  | M539281 | 99045 | GP1409388 | STANDARD ROLLER KIT | Kohler Plumbing | 6 | 488 | 0 | 488 | 2026-04-24 | STF-SMB |  | 130.5238 | 1011 | Green | Y | 2026-03-30 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539330 | 99097 | 70-0091-6610-2 | MR02-BN-ES Modern Ref Med Hook | 3M ACCOUNTS PAYABLE | 11 | 4480 | 0 | 4480 | 2026-04-24 | STF-8ST |  | 205.6205 | 2550 | Green | Y | 2026-03-30 10:19 |  |  | 1120 | 560 | Y |  |  | St Francis |  | STF-8ST
N |  | M539331 | 99098 | 70-0091-6620-1 | 17051BN-ES TRADITIONAL MEDIUM HOOK | 3M ACCOUNTS PAYABLE | 11 | 1728 | 0 | 1728 | 2026-04-24 | STF-8ST |  | 148.8 | 1951 | Green | Y | 2026-03-30 10:19 |  |  | 432 | 143.424 | Y |  | SF | St Francis
N |  | M539332 | 99099 | 70-0091-6669-8 | MR02-ORB-EF Mod Rf Md Mt Hk Oil Rb Bz | 3M ACCOUNTS PAYABLE | 11 | 2240 | 0 | 2240 | 2026-04-24 | STF-8ST |  | 240 | 2550 | Green | Y | 2026-03-30 10:19 |  |  | 560 | 280 | Y |  |  | St Francis
N |  | M539412 | 99201 | GP85160 | FLAPPER KIT - KOHL PLUMB | Kohler Plumbing | 11 | 20400 | 0 | 20400 | 2026-04-24 | STF-16ST |  | 136.4455 | KP 391 | White | N | 2026-03-31 10:00 |  |  | 0 | 4080 |  |  | SF | St Francis
N |  | M539420 | 99212 | GP1198201 | VALVE KIT | Kohler Plumbing | 5 | 1600 | 0 | 1600 | 2026-04-24 | STF-SMB |  | 150.1159 | KP 387 | Green | Y | 2026-03-31 12:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539422 | 99215 | GP800820 | PBU SERVICE KIT | Kohler Plumbing | 11 | 2000 | 0 | 2000 | 2026-04-24 | STF-16ST | + | 91.4783 | KP 115 | Green | Y | 2026-03-31 13:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539231 | 98978 | 70-0091-1777-4 | 414H-48 EXTREME DS MTG TAPE 1IN X 48 IN | 3M SCOTCH | 11 | 3480 | 0 | 3480 | 2026-04-27 | STF-20S-L-BS |  | 227.36 | 367 | Green | Y | 2026-03-27 10:10 |  | 34-8728-0901-6-QPB4 | 580.116 | 289.884 | Y |  | SF | St Francis
N |  | M539234 | 98981 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 0 | 8400 | 2026-04-27 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-03-27 10:10 |  | 34-8727-4490-8-QPB4 | 0 | 699.72 |  | Y | SF | St Francis
N |  | M539320 | 99086 | 70-0091-2714-6 | 114S Indoor DS MTG Tape 1 in x 50 in | 3M SCOTCH | 11 | 14400 | 0 | 14400 | 2026-04-27 | STF-20S-L-BS |  | 282.7925 | 367 | Green | Y | 2026-03-30 10:19 |  | 34-8727-2939-6-QPB4 | 2400.48 | 1199.52 | Y | Y | SF | St Francis
N |  | M539431 | 99228 | RGP77005-RP | VALVE KIT - RF | Kohler Plumbing | 7 | 2160 | 0 | 2160 | 2026-04-27 | STF-RF |  | 44.8183 | T6-008 | White | N | 2026-04-01 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539433 | 99230 | GP77006-RP | VALVE KIT CCW CLOSE | Kohler Plumbing | 10 | 8000 | 0 | 8000 | 2026-04-27 | STF-16ST |  | 184.8741 | KP 194 | Green | Y | 2026-04-01 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M537980 | 97116 | 70-0069-5847-7 | RF7053 Indoor Fasteners | 3M SCOTCH | 14 | 3840 | 0 | 3840 | 2026-04-28 | STF-16ST |  | 101.6869 | 424 | White | N | 2026-02-23 09:55 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M538521 | 97979 | 60-4550-5682-4 | PN03439 CLEAR REPAIR TAPE 1.5 IN X 115 IN 24/CASE V11 | 3M AUTO TAPE | 11 | 2160 | 0 | 2160 | 2026-04-28 | STF-16ST |  | 246.8571 | 404 | Green | Y | 2026-03-10 09:39 |  |  | 0 | 179.928 |  |  | SF | St Francis
N |  | M539303 | 99069 | 70-0069-6048-1 | 214P-CFT INDOOR MOUNTING TAPE | 3M SCOTCH | 11 | 7200 | 0 | 7200 | 2026-04-28 | STF-16ST |  | 158.2418 | 378 | Green | Y | 2026-03-30 10:18 |  |  | 1800 | 599.76 | Y |  | SF | St Francis
N |  | M539305 | 99071 | 70-0069-4893-2 | 4013-CFT SCOTCH FOAM MOUNTING TAPE 1/2" | 3M SCOTCH | 6 | 3864 | 0 | 3864 | 2026-04-28 | STF-LMB |  | 147.4546 | 380 | Green | N | 2026-03-30 10:18 |  |  | 644.1288 | 321.8712 | Y |  | SF | St Francis
N |  | M539306 | 99072 | 70-0069-5763-6 | RF7020-ALT Indoor Fasteners | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-04-28 | STF-16ST |  | 175.5486 | 424 | Green | Y | 2026-03-30 10:18 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539307 | 99073 | 70-0091-1386-4 | 414H EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 13920 | 0 | 13920 | 2026-04-28 | STF-20S-L-BS |  | 283.4888 | 367 | Green | Y | 2026-03-30 10:18 |  | 34-8728-9151-9-QPB4 | 2320.464 | 1159.536 | Y | Y | SF | St Francis
N |  | M539308 | 99074 | 70-0091-1388-0 | 214H Indoor DS MTG Tape 1in x 55in | 3M SCOTCH | 11 | 20880 | 0 | 20880 | 2026-04-28 | STF-20S-L-BR |  | 271.1143 | 367 | Green | Y | 2026-03-30 10:18 |  | 34-8727-2939-6-QPB4 | 3480.696 | 1739.304 | Y | Y | SF | St Francis
N |  | M539309 | 99075 | 70-0091-1777-4 | 414H-48 EXTREME DS MTG TAPE 1IN X 48 IN | 3M SCOTCH | 11 | 3480 | 0 | 3480 | 2026-04-28 | STF-20S-L-BS |  | 227.36 | 367 | Green | Y | 2026-03-30 10:18 |  | 34-8728-0901-6-QPB4 | 580.116 | 289.884 | Y |  | SF | St Francis
N |  | M539310 | 99076 | 70-0091-2502-5 | 110S-SR INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 7560 | 0 | 7560 | 2026-04-28 | STF-16ST |  | 216.2758 | 374 | Yellow | Y | 2026-03-30 10:18 |  | 34-8727-2939-6-QPB4 | 0 | 420.336 |  | Y | SF | St Francis
N |  | M539311 | 99077 | 70-0091-2504-1 | 314S-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 7200 | 0 | 7200 | 2026-04-28 | STF-16ST |  | 193.7104 | 372 | Yellow | N | 2026-03-30 10:18 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M539312 | 99078 | 70-0091-2507-4 | 410H CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3480 | 0 | 3480 | 2026-04-28 | STF-20S-L-BS |  | 227.0665 | 367 | Green | Y | 2026-03-30 10:18 |  | 34-8727-4490-8-QPB4 | 580.116 | 289.884 | Y | Y | SF | St Francis
N |  | M539313 | 99079 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 0 | 8400 | 2026-04-28 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-03-30 10:18 |  | 34-8727-4490-8-QPB4 | 0 | 699.72 |  | Y | SF | St Francis
N |  | M539316 | 99082 | 70-0091-2621-3 | 410H-DC-EF CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 2400 | 0 | 2400 | 2026-04-28 | STF-20S-L-BR |  | 250.4065 | 367 | Green | Y | 2026-03-30 10:19 |  | 34-8727-4490-8-QPB4 | 0 | 199.92 |  | Y | SF | St Francis
N |  | M539318 | 99084 | 70-0091-2657-7 | 410S-SR CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-04-28 | STF-20S-L-BR |  | 277.2 | 367 | Green | Y | 2026-03-30 10:19 |  | 34-8727-4490-8-QPB4 | 0 | 168.1344 |  | Y | SF | St Francis
N |  | M539319 | 99085 | 70-0091-2714-6 | 114S Indoor DS MTG Tape 1 in x 50 in | 3M SCOTCH | 11 | 14400 | 0 | 14400 | 2026-04-28 | STF-20S-L-BS |  | 282.7925 | 367 | Green | Y | 2026-03-30 10:19 |  | 34-8727-2939-6-QPB4 | 2400.48 | 1199.52 | Y | Y | SF | St Francis
N |  | M539322 | 99088 | 70-0091-4902-5 | RF4720-ALT Indoor Fasteners 7/8inx7/8in | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-04-28 | STF-16ST |  | 160.6902 | 424 | Yellow | N | 2026-03-30 10:19 |  |  | 960 | 319.872 | Y |  |  | St Francis
N |  | M539398 | 99187 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 19200 | 0 | 19200 | 2026-04-28 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-03-31 08:54 |  | 34-8728-9151-9-QPB4 | 0 | 1599.36 |  | Y | SF | St Francis
N |  | M539454 | 99254 | 70-0091-2711-2 | 859S REMOVABLE DS MTG SQUARES | 3M SCOTCH | 11 | 10752 | 0 | 10752 | 2026-04-28 | STF-16ST |  | 208.1006 | 376 | Yellow | N | 2026-04-01 16:07 |  |  | 1792.3584 |  | Y |  | SF | St Francis
N |  | M539504 | 99316 | GP1217811 | SMALL URINAL STRAINER | Kohler Plumbing | 5 | 1200 | 0 | 1200 | 2026-04-28 | STF-SMB |  | 130.9196 | 237 | Green | Y | 2026-04-02 13:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539549 | 99381 | 70-0091-2501-7-SUB | 110S INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 1896 | 0 | 1896 | 2026-04-28 | STF-16ST | + | 218 | 374 | Green | Y | 2026-04-03 10:16 |  | 34-8727-2939-6-QPB4 | 316.0632 |  |  |  |  | St Francis
N |  | M539631 | 99489 | 70-0091-3481-1 | 410S-ESF CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-04-28 | STF-20S-L-BS |  | 263.2104 | 367 | Yellow | N | 2026-04-06 10:41 |  | 34-8727-4490-8-QPB4 | 600.12 | 299.88 | Y | Y | SF | St Francis
N |  | M539746-1 | 99717 | RGP800820-PB | PBU SERVICE KIT | Kohler Plumbing | 2 | 2000 | 0 | 2000 | 2026-04-28 | ABM |  | 151.8519 |  | Green | Y | 2026-04-09 10:13 |  |  | 0 |  |  |  | SF | Morris
N |  | M539072 | 98756 | 24 755 66-S | KIT VALVE TRAIN | DISCOVERY ENERGY LLC | 2 | 300 | 0 | 300 | 2026-04-29 | AB/ABM |  | 29.34 |  | Green | Y | 2026-03-24 09:00 |  |  | 0 | 12 |  |  | SF | Morris
N |  | M539256 | 99003 | 32 841 02-S | KIT CYLINDER HEAD GASKET | DISCOVERY ENERGY LLC | 2 | 4000 | 0 | 4000 | 2026-04-29 | AB |  | 89.3357 |  | Green | Y | 2026-03-27 15:00 |  |  | 0 | 80 |  |  | SF | St Francis
N |  | M539269 | 99016 | 12 883 05-S1 | SHORT TRIANGLE AIR FILTERS | DISCOVERY ENERGY LLC | 6 | 1911 | 0 | 1911 | 2026-04-29 | STF-6ST |  | 87.6667 |  | Yellow | N | 2026-03-27 15:01 |  |  | 0 | 47.775 |  |  | SF | St Francis
N |  | M539411 | 99200 | 14 132 11-S1 | SPARK PLUG BLISTER CARD PKG | DISCOVERY ENERGY LLC | 5 | 3000 | 0 | 3000 | 2026-04-29 | SMB |  | 181.3637 |  | Green | N | 2026-03-31 10:00 |  |  | 0 |  |  |  | SF | Morris
N |  | M539449 | 99249 | 70-0069-6055-6 | RF7170X-ALT INDOOR FASTENERS | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-04-30 | STF-16ST |  | 106.2966 | 424 | Yellow | N | 2026-04-01 16:07 |  |  | 756 | 504.1008 | Y |  | SF | St Francis
N |  | M539451 | 99251 | 70-0091-1386-4 | 414H EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 13920 | 0 | 13920 | 2026-04-30 | STF-20S-L-BS |  | 283.4888 | 367 | Green | Y | 2026-04-01 16:07 |  | 34-8728-9151-9-QPB4 | 2320.464 | 1159.536 | Y | Y | SF | St Francis
N |  | M539452 | 99252 | 70-0091-1806-1 | 110H INDOOR DS MTG TAPE .5IN X X80IN | 3M SCOTCH | 11 | 16800 | 0 | 16800 | 2026-04-30 | STF-16ST |  | 241.1794 | 374 | Green | Y | 2026-04-01 16:07 |  | 34-8727-2939-6-QPB4 | 2800.56 | 1399.44 | Y | Y | SF | St Francis
N |  | M539453 | 99253 | 70-0091-2500-9 | 410S Clear DS MTG Tape 1in x 60in | 3M SCOTCH | 11 | 7200 | 0 | 7200 | 2026-04-30 | STF-20S-L-BS |  | 322.7027 | 367 | Green | Y | 2026-04-01 16:07 |  | 34-8727-4490-8-QPB4 | 1200.24 | 599.76 | Y | Y | SF | St Francis
N |  | M539484 | 99292 | 70-0091-2501-7 | 110S INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 18000 | 0 | 18000 | 2026-04-30 | STF-16ST |  | 276.0821 | 374 | Yellow | N | 2026-04-02 09:53 |  | 34-8727-2939-6-QPB4 | 3000.6 |  | Y | Y | SF | St Francis
N |  | M539485 | 99293 | 70-0091-2507-4 | 410H CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3480 | 0 | 3480 | 2026-04-30 | STF-20S-L-BS |  | 227.0665 | 367 | Green | Y | 2026-04-02 09:53 |  | 34-8727-4490-8-QPB4 | 580.116 | 289.884 | Y | Y | SF | St Francis
N |  | M539317 | 99083 | 70-0091-2623-9 | 110H-DC-EF INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 12 | 1200 | 0 | 1200 | 2026-05-01 | STF-16ST |  | 369.2308 | 374 | Green | Y | 2026-03-30 10:19 |  | 34-8727-2939-6-QPB4 | 0 | 99.96 |  | Y | SF | St Francis
N |  | M539538 | 99370 | 70-0091-6620-1 | 17051BN-ES TRADITIONAL MEDIUM HOOK | 3M ACCOUNTS PAYABLE | 11 | 1728 | 0 | 1728 | 2026-05-01 | STF-8ST |  | 148.8 | 1951 | Green | Y | 2026-04-03 10:16 |  |  | 432 | 143.424 | Y |  | SF | St Francis
N |  | M539567 | 99418 | GP1016515 | VALVE KIT - KOHLER PLUM | Kohler Plumbing | 11 | 2700 | 0 | 2700 | 2026-05-01 | STF-16ST | P | 190.171 | KP 387 | Yellow | N | 2026-04-06 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539568 | 99419 | GP1409394 | CENTER GUIDE KIT | Kohler Plumbing | 5 | 893 | 0 | 893 | 2026-05-01 | STF-SMB |  | 98.8854 |  | Green | Y | 2026-04-06 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539569 | 99420 | GP1017426 | LONG VALVE - KOHLER PLUM | Kohler Plumbing | 11 | 2240 | 0 | 2240 | 2026-05-01 | STF-16ST | + | 145.0765 | KP 387 | Green | Y | 2026-04-06 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539579 | 99437 | 70-0091-6322-4 | 17047-ES STKY NL SWTTH HNGR | 3M ACCOUNTS PAYABLE | 11 | 11520 | 0 | 11520 | 2026-05-01 | STF-8ST |  | 148.2754 | 2761 | Green | Y | 2026-04-06 10:40 |  |  | 2880 | 959.616 | Y |  | SF | St Francis
N |  | M539580 | 99438 | 70-0091-6620-1 | 17051BN-ES TRADITIONAL MEDIUM HOOK | 3M ACCOUNTS PAYABLE | 11 | 1728 | 0 | 1728 | 2026-05-01 | STF-8ST |  | 148.8 | 1951 | Green | Y | 2026-04-06 10:40 |  |  | 432 | 143.424 | Y |  | SF | St Francis
N |  | M539581 | 99439 | 70-0091-8640-7 | 17005-ES Spring Clip | 3M ACCOUNTS PAYABLE | 11 | 2160 | 0 | 2160 | 2026-05-01 | STF-8ST |  | 162.9434 | SEAL TOOL ID, ALGUS 1081 | Green | Y | 2026-04-06 10:40 |  |  | 358.56 | 118.8 | Y |  | SF | St Francis
N |  | M539582 | 99440 | 70-0091-8718-1 | MR02-SN-B MOD REFL NKL 1HK 2WTR-RST-STRP | 3M ACCOUNTS PAYABLE | 11 | 960 | 0 | 960 | 2026-05-01 | STF-8ST |  | 267 | 2550 | Yellow | N | 2026-04-06 10:41 |  |  | 240 | 120 | Y |  |  | St Francis
N |  | M539630 | 99488 | 70-0091-2855-7 | 110S-ESF INDOOR DS MTG TAPE 1/2IN X 80IN | 3M SCOTCH | 11 | 6000 | 0 | 6000 | 2026-05-01 | STF-16ST |  | 293.3637 | 374 | Green | Y | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 1000.2 | 499.8 | Y | Y | SF | St Francis
N |  | M539636 | 99494 | GP876851 | PBU/CAP SERVICE KIT | Kohler Plumbing | 11 | 5000 | 0 | 5000 | 2026-05-01 | STF-16ST | + | 36.6733 | KP 024 | Green | N | 2026-04-06 11:00 |  |  | 0 |  |  |  | SF | St Francis |  | STF-16ST-B
N |  | M539769 | 99706 | 70-0091-3481-1 | 410S-ESF CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 7200 | 0 | 7200 | 2026-05-01 | STF-20S-L-BS |  | 263.2104 | 367 | Yellow | N | 2026-04-09 09:45 |  | 34-8727-4490-8-QPB4 | 1200.24 | 599.76 | Y | Y | SF | St Francis
N |  | M539546 | 99378 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 0 | 8400 | 2026-05-04 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-04-03 10:16 |  | 34-8727-4490-8-QPB4 | 0 | 699.72 |  | Y | SF | St Francis
N |  | M539548 | 99380 | 70-0091-2710-4 | 414S-48 EXTREME DS MTG TAPE 1IN 48IN | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-05-04 | STF-20S-L-BS |  | 257.3055 | 367 | Green | Y | 2026-04-03 10:16 |  | 34-8728-0901-6-QPB4 | 600.12 | 299.88 | Y |  | SF | St Francis
N |  | M539715 | 99638 | RGP1198201 | VALVE KIT | Kohler Plumbing | 0 | 1000 | 0 | 1000 | 2026-05-04 | STF-RF |  | 55.0534 | T6-009 | White | Y | 2026-04-08 09:00 |  |  | 0 |  |  |  |  | St Francis
N |  | M539716 | 99639 | GP1013092-96 | BOLT CAP ASSY - KOHLER PLUM | Kohler Plumbing | 9 | 1000 | 0 | 1000 | 2026-05-04 | STF-16ST |  | 133.8304 | KP 387 | Pink | N | 2026-04-08 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M538735 | 98274 | 70-0069-3429-6 | 16736NA Cld WthrElecTp 0.75inX25ft 24/cs | 3M ELECTRICAL TAPE | 9 | 16800 | 0 | 16800 | 2026-05-05 | STF-16ST |  | 337.9572 | 403 | Pink | N | 2026-03-13 08:59 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539227 | 98974 | 70-0069-3428-8 | 194NA Spr 33+ElcTp,.5 in X 5.5 yd, 24/cs | 3M ELECTRICAL TAPE | 11 | 1728 | 0 | 1728 | 2026-05-05 | STF-16ST |  | 192.5944 | 406 | Pink | N | 2026-03-27 10:10 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539399 | 99188 | 70-0069-9103-1-N | (1) 47200-HZ6-NA 3M(TM) PERFORMANCE EYEWEAR GASKET (2) DESIGN, MIRROR LENS, ANTI-FOG, 6EA/CSS | 3M EYEWEAR | 11 | 3528 | 0 | 3528 | 2026-05-05 | STF-16ST |  | 155.0769 | 460 | Green | Y | 2026-03-31 08:54 |  | 34-2001-6584-2-QPB4 | 0 | 1175.8824 |  |  | SF | St Francis
N |  | M539592 | 99450 | 70-0069-3410-6 | 03429NA 700 Elctrcl Tp, .75inX66ft 24/cs | 3M ELECTRICAL TAPE | 10 | 3600 | 0 | 3600 | 2026-05-05 | STF-16ST |  | 268.9727 | 409 | Green | Y | 2026-04-06 10:41 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539610 | 99468 | 70-0091-1386-4 | 414H EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 20880 | 0 | 20880 | 2026-05-05 | STF-20S-L-BS |  | 283.4888 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8728-9151-9-QPB4 | 3480.696 | 1739.304 | Y | Y | SF | St Francis
N |  | M539611 | 99469 | 70-0091-1388-0 | 214H Indoor DS MTG Tape 1in x 55in | 3M SCOTCH | 11 | 20880 | 0 | 20880 | 2026-05-05 | STF-20S-L-BR |  | 271.1143 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 3480.696 | 1739.304 | Y | Y | SF | St Francis
N |  | M539612 | 99470 | 70-0091-1777-4 | 414H-48 EXTREME DS MTG TAPE 1IN X 48 IN | 3M SCOTCH | 11 | 6960 | 0 | 6960 | 2026-05-05 | STF-20S-L-BS |  | 227.36 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8728-0901-6-QPB4 | 1160.232 | 579.768 | Y |  | SF | St Francis
N |  | M539614 | 99472 | 70-0091-1806-1 | 110H INDOOR DS MTG TAPE .5IN X X80IN | 3M SCOTCH | 11 | 16800 | 0 | 16800 | 2026-05-05 | STF-16ST |  | 241.1794 | 374 | Yellow | Y | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 2800.56 | 1399.44 | Y | Y | SF | St Francis
N |  | M539615 | 99473 | 70-0091-2501-7 | 110S INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 18000 | 0 | 18000 | 2026-05-05 | STF-16ST |  | 276.0821 | 374 | Yellow | N | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 3000.6 |  | Y | Y | SF | St Francis
N |  | M539616 | 99474 | 70-0091-2502-5 | 110S-SR INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 4536 | 0 | 4536 | 2026-05-05 | STF-16ST |  | 216.2758 | 374 | Yellow | Y | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 0 | 252.2016 |  | Y | SF | St Francis
N |  | M539617 | 99475 | 70-0091-2503-3 | 314S-MED-SR INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 7560 | 0 | 7560 | 2026-05-05 | STF-16ST |  | 176.9934 | 372 | Yellow | N | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M539618 | 99476 | 70-0091-2504-1 | 314S-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 7200 | 0 | 7200 | 2026-05-05 | STF-16ST |  | 193.7104 | 372 | Yellow | N | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M539619 | 99477 | 70-0091-2507-4 | 410H CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 13920 | 0 | 13920 | 2026-05-05 | STF-20S-L-BS |  | 227.0665 | 367 | Yellow | Y | 2026-04-06 10:41 |  | 34-8727-4490-8-QPB4 | 2320.464 | 1159.536 | Y | Y | SF | St Francis
N |  | M539620 | 99478 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 0 | 8400 | 2026-05-05 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-4490-8-QPB4 | 0 | 699.72 |  | Y | SF | St Francis
N |  | M539621 | 99479 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 12000 | 0 | 12000 | 2026-05-05 | STF-20S-L-BR |  | 299.0769 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-4490-8-QPB4 | 0 | 999.6 |  | Y | SF | St Francis
N |  | M539624 | 99482 | 70-0091-2618-9 | 414H-DC-EF EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 4800 | 0 | 4800 | 2026-05-05 | STF-20S-L-BR |  | 242.449 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8728-9151-9-QPB4 | 0 | 399.84 |  | Y | SF | St Francis
N |  | M539625 | 99483 | 70-0091-2620-5 | 214H-DC-EF Indoor DS MTG Tape 1in x 55in | 3M SCOTCH | 12 | 1200 | 0 | 1200 | 2026-05-05 | STF-20S-L-BR |  | 213.4387 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 0 | 99.96 |  | Y | SF | St Francis
N |  | M539626 | 99484 | 70-0091-2621-3 | 410H-DC-EF CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 2400 | 0 | 2400 | 2026-05-05 | STF-20S-L-BR |  | 250.4065 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-4490-8-QPB4 | 0 | 199.92 |  | Y | SF | St Francis
N |  | M539627 | 99485 | 70-0091-2657-7 | 410S-SR CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 3024 | 0 | 3024 | 2026-05-05 | STF-20S-L-BR |  | 277.2 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-4490-8-QPB4 | 0 | 168.1344 |  | Y | SF | St Francis
N |  | M539628 | 99486 | 70-0091-2714-6 | 114S Indoor DS MTG Tape 1 in x 50 in | 3M SCOTCH | 11 | 18000 | 0 | 18000 | 2026-05-05 | STF-20S-L-BS |  | 282.7925 | 367 | Green | Y | 2026-04-06 10:41 |  | 34-8727-2939-6-QPB4 | 3000.6 | 1499.4 | Y | Y | SF | St Francis
N |  | M539632 | 99490 | 70-0069-9274-0 | RF7020X SCOTCH(R) INDOOR FASTENERS | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-05-05 | STF-16ST |  | 157.5426 | 424 | Yellow | Y | 2026-04-06 10:41 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539635 | 99493 | 70-0069-5763-6 | RF7020-ALT Indoor Fasteners | 3M SCOTCH | 11 | 3840 | 0 | 3840 | 2026-05-05 | STF-16ST |  | 175.5486 | 424 | Yellow | Y | 2026-04-06 10:41 |  |  | 960 | 319.872 | Y |  | SF | St Francis
N |  | M539664 | 99554 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 16800 | 0 | 16800 | 2026-05-05 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-04-07 08:40 |  | 34-8728-9151-9-QPB4 | 0 | 1399.44 |  | Y | SF | St Francis
N |  | M539729 | 99652 | 70-0069-4893-2 | 4013-CFT SCOTCH FOAM MOUNTING TAPE 1/2" | 3M SCOTCH | 6 | 552 | 0 | 552 | 2026-05-05 | STF-LMB |  | 147.4546 | 380 | Green | Y | 2026-04-08 09:29 |  |  | 92.0184 | 45.9816 | Y |  | SF | St Francis
N |  | M539745 | 99681 | GP800820 | PBU SERVICE KIT | Kohler Plumbing | 11 | 2000 | 0 | 2000 | 2026-05-05 | STF-16ST | + | 91.4783 | KP 115 | Green | Y | 2026-04-09 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539746 | 99682 | RGP800820 | PBU SERVICE KIT | Kohler Plumbing | 10 | 2000 | 0 | 2000 | 2026-05-05 | RF | P | 26.441 | T6-012 | Pink | N | 2026-04-09 09:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539727 | 99650 | 70-0069-3415-5 | 10414NA Spr 33+ Elc Tp .75X450in 24/cs | 3M ELECTRICAL TAPE | 11 | 1200 | 0 | 1200 | 2026-05-06 | STF-16ST |  | 103.8638 | 407 | Green | Y | 2026-04-08 09:29 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539736 | 99665 | 12 883 10-S1 | TALL TRIANGLE AIR FILTERS | DISCOVERY ENERGY LLC | 5 | 3456 | 0 | 3456 | 2026-05-06 | STF-SMB |  | 80.6958 | QPI3042 | Yellow | N | 2026-04-08 11:00 |  |  | 0 | 141.696 |  |  | SF | St Francis
N |  | M539768 | 99705 | 70-0091-8527-6 | 410-MED-DC-EF | 3M ACCOUNTS PAYABLE | 11 | 864 | 0 | 864 | 2026-05-06 | STF-16ST |  | 209.647 | 372 | Green | Y | 2026-04-09 09:45 |  | 34-8727-4490-8-QPB4 | 0 | 71.9712 |  | Y | SF | St Francis |  | STF-16ST-C
N |  | M539789 | 99747 | 32 883 09-S1 | SHORT AIR FILTER | DISCOVERY ENERGY LLC | 5 | 4320 | 0 | 4320 | 2026-05-06 | STF-SMB |  | 114.2908 | 13QP0312A3/118 | Green | Y | 2026-04-09 14:00 |  |  | 0 | 432 |  |  | SF | St Francis
N |  | M539790 | 99748 | 24 050 13-S1 | FUEL FILTER - KOHLER | DISCOVERY ENERGY LLC | 8 | 4200 | 0 | 4200 | 2026-05-06 | 6ST |  | 228.8903 | 307 | Yellow | N | 2026-04-09 14:00 |  |  | 0 | 168 |  |  | SF | St Francis
N |  | M539807 | 99778 | 45 883 02-C | KOHLER TRAY PACK | DISCOVERY ENERGY LLC | 9 | 800 | 0 | 800 | 2026-05-06 | STF-16ST |  | 68.5926 | 184 | Yellow | N | 2026-04-10 09:00 |  |  | 0 | 160 |  |  | SF | St Francis
N |  | M539859 | 99909 | 70-0091-2711-2 | 859S REMOVABLE DS MTG SQUARES | 3M SCOTCH | 11 | 10752 | 0 | 10752 | 2026-05-07 | STF-16ST |  | 208.1006 | 376 | Yellow | N | 2026-04-10 16:00 |  |  | 1792.3584 |  | Y |  | SF | St Francis
N |  | M539860 | 99910 | 70-0091-2502-5 | 110S-SR INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 1512 | 0 | 1512 | 2026-05-07 | STF-16ST |  | 216.2758 | 374 | Yellow | Y | 2026-04-10 16:00 |  | 34-8727-2939-6-QPB4 | 0 | 84.0672 |  | Y | SF | St Francis
N |  | M539861 | 99911 | 70-0091-1806-1 | 110H INDOOR DS MTG TAPE .5IN X X80IN | 3M SCOTCH | 11 | 16800 | 0 | 16800 | 2026-05-07 | STF-16ST |  | 241.1794 | 374 | Yellow | Y | 2026-04-10 16:00 |  | 34-8727-2939-6-QPB4 | 2800.56 | 1399.44 | Y | Y | SF | St Francis
N |  | M539862 | 99912 | 70-0091-1780-8 | 314H-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 7680 | 0 | 7680 | 2026-05-07 | STF-16ST |  | 185.4846 | 372 | Green | Y | 2026-04-10 16:00 |  | 34-8727-2939-6-QPB4 | 1280.256 | 639.744 | Y | Y | SF | St Francis
N |  | M539863 | 99913 | 70-0091-1386-4 | 414H EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 13920 | 0 | 13920 | 2026-05-07 | STF-20S-L-BS |  | 283.4888 | 367 | Green | Y | 2026-04-10 16:00 |  | 34-8728-9151-9-QPB4 | 2320.464 | 1159.536 | Y | Y | SF | St Francis
N |  | M539878 | 99942 | 60-4550-5627-9 | PN03410 MOUNTING TAPE 1/2 IN x 75 IN 24 ROLLS/CASE V11 | 3M AUTO TAPE | 9 | 6048 | 0 | 6048 | 2026-05-08 | STF-16ST |  | 300.6261 | 405 | Yellow | N | 2026-04-13 09:32 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539898 | 99962 | 70-0069-5589-5 | 4013-CFT-ESF FOAM MOUNTING TAPE | 3M SCOTCH | 11 | 3864 | 0 | 3864 | 2026-05-08 | STF-LMB |  | 230.9451 | 380 | Yellow | N | 2026-04-13 09:33 |  |  | 644.1288 | 321.8712 | Y |  | SF | St Francis
N |  | M539899 | 99963 | 70-0069-6048-1 | 214P-CFT INDOOR MOUNTING TAPE | 3M SCOTCH | 11 | 3600 | 0 | 3600 | 2026-05-08 | STF-16ST |  | 158.2418 | 378 | Green | Y | 2026-04-13 09:33 |  |  | 900 | 299.88 | Y |  | SF | St Francis
N |  | M539900 | 99964 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 12000 | 0 | 12000 | 2026-05-08 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-04-13 09:33 |  | 34-8728-9151-9-QPB4 | 0 | 999.6 |  | Y | SF | St Francis
N |  | M539901 | 99965 | 70-0091-1384-9 | 414H-DC EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 12000 | 0 | 12000 | 2026-05-08 | STF-20S-L-BR |  | 264.1214 | 367 | Green | Y | 2026-04-13 09:33 |  | 34-8728-9151-9-QPB4 | 0 | 999.6 |  | Y | SF | St Francis
N |  | M539902 | 99966 | 70-0091-1386-4 | 414H EXTREME DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 13920 | 0 | 13920 | 2026-05-08 | STF-20S-L-BS |  | 283.4888 | 367 | Green | Y | 2026-04-13 09:33 |  | 34-8728-9151-9-QPB4 | 2320.464 | 1159.536 | Y | Y | SF | St Francis
N |  | M539905 | 99969 | 70-0091-2502-5 | 110S-SR INDOOR DS MTG TAPE 0.5IN X 80IN | 3M SCOTCH | 11 | 4536 | 0 | 4536 | 2026-05-08 | STF-16ST |  | 216.2758 | 374 | Yellow | Y | 2026-04-13 09:33 |  | 34-8727-2939-6-QPB4 | 0 | 252.2016 |  | Y | SF | St Francis
N |  | M539906 | 99970 | 70-0091-2507-4 | 410H CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 6960 | 0 | 6960 | 2026-05-08 | STF-20S-L-BS |  | 227.0665 | 367 | Pink | Y | 2026-04-13 09:33 |  | 34-8727-4490-8-QPB4 | 1160.232 | 579.768 | Y | Y | SF | St Francis
N |  | M539907 | 99971 | 70-0091-2508-2 | 410H-DC CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 12 | 8400 | 0 | 8400 | 2026-05-08 | STF-20S-L-BR |  | 299.0769 | 367 | White | Y | 2026-04-13 09:33 |  | 34-8727-4490-8-QPB4 | 0 | 699.72 |  | Y | SF | St Francis
N |  | M539908 | 99972 | 70-0091-2512-4 | 410H-MED-DC INDOOR DS MTG TAPE 1IN X 125IN | 3M SCOTCH | 11 | 2592 | 0 | 2592 | 2026-05-08 | STF-16ST |  | 175.7605 | 372 | Green | Y | 2026-04-13 09:33 |  | 34-8727-4490-8-QPB4 | 0 | 215.9136 |  | Y | SF | St Francis
N |  | M539910 | 99974 | 70-0091-2657-7 | 410S-SR CLEAR DS MTG TAPE 1IN X 60IN | 3M SCOTCH | 11 | 4536 | 0 | 4536 | 2026-05-08 | STF-20S-L-BR |  | 277.2 | 367 | White | Y | 2026-04-13 09:33 |  | 34-8727-4490-8-QPB4 | 0 | 252.2016 |  | Y | SF | St Francis
N |  | M539911 | 99975 | 70-0091-2712-0 | 859S-SR REMOVABLE DS MTG SQUARES | 3M SCOTCH | 11 | 10368 | 0 | 10368 | 2026-05-08 | STF-16ST |  | 190.8517 | 376 | Yellow | Y | 2026-04-13 09:33 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539922 | 99989 | GP53410 | GASKET URINAL 1PC TOILETS | Kohler Plumbing | 5 | 2000 | 0 | 2000 | 2026-05-08 | STF-SMB |  | 164.9831 | 4020 | White | N | 2026-04-13 10:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539013 | 98697 | 70-0069-3426-2 | 200NA Electrical Tp,0.75inX12.5yd, 24/cs | 3M ELECTRICAL TAPE | 8 | 6048 | 0 | 6048 | 2026-05-12 | STF-16ST |  | 231.0301 | 402 | Green | Y | 2026-03-23 15:01 |  |  | 1008.2016 |  | Y |  | SF | St Francis
N |  | M539076 | 98760 | 70-0069-3426-2 | 200NA Electrical Tp,0.75inX12.5yd, 24/cs | 3M ELECTRICAL TAPE | 8 | 6048 | 0 | 6048 | 2026-05-12 | STF-16ST |  | 231.0301 | 402 | Green | Y | 2026-03-24 10:01 |  |  | 1008.2016 |  | Y |  | SF | St Francis
N |  | M539077 | 98761 | 70-0069-3426-2 | 200NA Electrical Tp,0.75inX12.5yd, 24/cs | 3M ELECTRICAL TAPE | 8 | 6048 | 0 | 6048 | 2026-05-12 | STF-16ST |  | 231.0301 | 402 | Green | Y | 2026-03-24 10:01 |  |  | 1008.2016 |  | Y |  | SF | St Francis
N |  | M539255 | 99002 | 62 132 04-S | PLUG SPARK | DISCOVERY ENERGY LLC | 2 | 2196 | 0 | 2196 | 2026-05-13 | AB/ABM |  | 103.9916 |  | White | N | 2026-03-27 15:00 |  |  | 0 |  |  |  | SF | Morris
N |  | M539266 | 99013 | 14 083 19-S | ELEMENT AIR FILTER | DISCOVERY ENERGY LLC | 2 | 1600 | 0 | 1600 | 2026-05-13 | AB |  | 194.1176 |  | White | Y | 2026-03-27 15:01 |  |  | 0 | 160 |  |  | SF | St Francis
N |  | M539276 | 99036 | 25 132 14-S | SPARK PLUG | DISCOVERY ENERGY LLC | 2 | 960 | 0 | 960 | 2026-05-13 | AB/ABM |  | 107.2706 |  | Green | Y | 2026-03-27 16:00 |  |  | 0 |  |  |  | SF | Morris
N |  | M538929 | 98574 | GP1043211-VS | SIMPLICE SPRAYHEAD | Kohler Plumbing | 5 | 1300 | 0 | 1300 | 2026-05-15 | STF-SMB |  | 128.3877 | 3025 | Green | Y | 2026-03-19 10:00 |  |  | 0 |  |  |  | SF | St Francis
N |  | M539400 | 99189 | 70-0091-8975-7-N | 47213H1-VDC-PS Eyewear, Blue/Clear, 5/CV | 3M EYEWEAR | 11 | 1280 | 0 | 1280 | 2026-05-20 | STF-16ST |  | 38.8383 | 461 | Pink | N | 2026-03-31 08:54 |  | 34-2001-6774-9-QPB4 | 0 | 256 |  |  | SF | St Francis
N |  | M539475 | 99283 | 70-0091-2504-1-SUB | 314S-MED INDOOR DS MTG TAPE 1IN X 125IN | 3M ACCOUNTS PAYABLE | 11 | 14000 | 0 | 14000 | 2026-05-20 | STF-16ST |  | 245.2869 | 372 | Yellow | N | 2026-04-02 07:48 |  | 34-8727-2939-6-QPB4 | 0 |  |  | Y | SF | St Francis
N |  | M539432 | 99229 | RGP77006-RP | VALVE KIT - RF | Kohler Plumbing | 10 | 1258 | 0 | 1258 | 2026-05-25 | RF |  | 46.3863 | T6-008 | Yellow | Y | 2026-04-01 09:00 |  |  | 0 |  |  |  | SF | St Francis